## Slide 1
Supporting Domestic Violence Adult Survivors and Their Children Through Partnership with Community-based Service Agencies

## Slide 2
Project Timeline
February Project leads attend 1st AAP webinar – February 23, 1 p.m. CT February 24, 2 p.m. – 2nd Leadership Call - Finalize schedule of webinars & topic ideas - Develop plan of communication to local partnership members March Project leads attend 2nd AAP webinar
March 10, 2 p.m. - 3rd Leadership Call - Finalize speakers and educational content for webinars
March 24, 2 p.m. – 4th Leadership Call - Establish final details for webinars - Report on local communication efforts

## Slide 3
Project Timeline
April Project leads attend 3rd AAP webinar
Week of April 4 – 1st educational webinar
April 14, 2 p.m. – 5th Leadership Call - Evaluate first webinar - Review plan for remaining webinars, pivot as needed
May
Week of May 2 – 2nd educational webinar
May 12, 2 p.m. – 6th Leadership Call - Begin evaluation of project
June
Week of June 6 – 3rd educational webinar
Week of June 20 – Final Leadership Call - Establish next steps for partnership - Contribute to progress report Summer/Fall 2022 – Panel discussions at state conferences to share blueprint

## Slide 4
Questions?
Linda Lee, AL-AAP – llee@alaap.org, 334-954-2543
Elizabeth Dawson, MD, FAAP – enelso71@gmail.com